## Sheet1
Task ID | Task Description | Assigned By | Assigned To | Priority | Start Date | Target Completion Date | Final Status | Actual Completion Date | Reason For Delay | Submitted To
TSK-001 | Create HR Dashboard | Manager A | Rahul | High | 2025-02-10 | 2025-02-15 | Pending | 2025-02-15 |  | Onboarding Team
TSK-002 | API Integration for Tasks | Manager B | Priya | Medium | 2025-02-12 | 2025-02-18 | In Progress |  |  | Tech Lead
TSK-003 | UI Bug Fixes | Manager A | Karthik | Low | 2025-02-14 | 2025-02-20 | Completed |  |  | QA Team
TSK-004 | Database Optimization | Manager C | Anitha | High | 2025-02-01 | 2025-02-10 | Delayed | 2025-02-14 | Server downtime | DB Admin
TSK-005 | Excel Upload Feature | Manager B | Suresh | Medium | 2025-02-16 | 2025-02-22 | In Progress | 2025-02-21 |  | HR Team